## User-StoriesProduct Backlog
ID | Theme | As a/an | I want to | so that | Notes | PRODUCT BACKLOG |  |  |  | SPRINT TASKS
[6 empty] | Priority | Status | Tasks # | Tasks | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
1 | Development | Developer | Creat a unique product designed for enterprises to quickly pick up and use | That can manage/track hours | [5 empty] | 5/5
[6 empty] | 1 | Complete | Task1 | Create development environment
[6 empty] | 2 | Complete | Task2 | Get IDE loaded
[6 empty] | 3 | Complete | Task3 | Create project in repository
[6 empty] | 4 | Complete | Task4 | Install SQL Server Management
[6 empty] | 5 | Complete | Task5 | Create Database
3 | Functional | User | Be able to log in using my employee ID number and my unique password | I can connect to my companies database and see my role and hours worked there. | [6 empty] | 7/7
[6 empty] | 6 | Complete | Task6 | Create a database table used for tracking the amount of hours employees have worked
[6 empty] | 7 | Complete | Task7 | Come up with company standard roles for the database. Such as CEO, HR, Sales, etc.
[6 empty] | 8 | Complete | Task8 | Create basic login GUI called LoginForm
[6 empty] | 9 | Complete | Task9 | Give the GUI the appropriate buttons, text boxes and labels.
[6 empty] | 10 | Complete | Task 10 | Create unique permissions for each unique role in database
[6 empty] | 11 | Complete | Task 11 | Create login and cancel button on the LoginForm
[6 empty] | 12 | Complete | Task 12 | Upload new code to repository
3 | Functional | Developer | Be able to validate data the user has input and output the appropriate data | Employees can securely login and see relavent information to them and thei role | [7 empty] | 11/9
[6 empty] | 13 | Complete | Task 13 | Create login method for text box 1 & 2
[6 empty] | 14 | Complete | Task14 | Connect the application to the database.
[6 empty] | 15 | Complete | Task 15 | Add MainForm for users to be directed to after successful login
[6 empty] | 16 | Complete | Task 16 | Give the MainForm a datagrid to display data.
[6 empty] | 17 | Complete | Task 17 | Add Clock in & Clock out button on the MainForm
[6 empty] | 18 | Complete | Task 18 | Give the input buttons functionality (Login/Cancel)
[6 empty] | 19 | Complete | Task 19 | Give Clock in & Clock out buttons functionality
[6 empty] | 20 | Complete | Task 20 | Conduct unit/integration testing on the Clock in & Clock out buttons
[6 empty] | 21 | Complete | Task 21 | Upload new code to repository
5 | Development | Developer | I would like to confirm the application is running efficiently and is effective | I can confirm the application is ready for deployment | [8 empty] | 4\4
[6 empty] | 22 | Complete | Task 22 | Test overall functionality of the application
[6 empty] | 23 | Complete | Task 23 | Revise/Refine the applications code
[6 empty] | 24 | Complete | Task 24 | Debug
[6 empty] | 25 | Complete | Task 25 | Upload code to repository

## Product Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2023-11-22 | 25 | 25 | Bold = completed.
Thu | 2023-11-23 | 24 | 24
Fri | 2023-11-24 | 24 | 24
Sat | 2023-11-25 | 23 | 23
Sun | 2023-11-26 | 23 | 23
Mon | 2023-11-27 | 22 | 22
Tue | 2023-11-28 | 22 | 22
Wed | 2023-11-29 | 22 | 22
Thu | 2023-11-30 | 22 | 22
Fri | 2023-12-01 | 22 | 22
Sat | 2023-12-02 | 21 | 21
Sun | 2023-12-03 | 21 | 21
Mon | 2023-12-04 | 21 | 21
Tue | 2023-12-05 | 20 | 20
Wed | 2023-12-06 | 20 | 20
Thu | 2023-12-07 | 19 | 20
Fri | 2023-12-08 | 18 | 18
Sat | 2023-12-09 | 18 | 18
Sun | 2023-12-10 | 18 | 18
Mon | 2023-12-11 | 17 | 17
Tue | 2023-12-12 | 16 | 17
Wed | 2023-12-13 | 15 | 17
Thu | 2023-12-14 | 14 | 17
Fri | 2023-12-15 | 13 | 16
Sat | 2023-12-16 | 13 | 16
Sun | 2023-12-17 | 13 | 16
Mon | 2023-12-18 | 13 | 15
Tue | 2023-12-19 | 13 | 14
Wed | 2023-12-27 | 13 | 14
Thu | 2023-12-28 | 12 | 13
Fri | 2023-12-29 | 11 | 11
Sat | 2023-12-30 | 11 | 10
Sun | 2023-12-31 | 11 | 10
Mon | 2024-01-01 | 10 | 10
Tue | 2024-01-02 | 9 | 8
Wed | 2024-01-03 | 8 | 7
Thu | 2024-01-04 | 7 | 7
Fri | 2024-01-05 | 6 | 7
Sat | 2024-01-06 | 5 | 7
Sun | 2024-01-07 | 5 | 6
Mon | 2024-01-08 | 4 | 5
Tue | 2024-01-09 | 4 | 4
Wed | 2024-01-03 | 4 | 4
Thu | 2024-01-04 | 3 | 4
Fri | 2024-01-05 | 2 | 4
Sat | 2024-01-06 | 2 | 3
Sun | 2024-01-07 | 1 | 3
Mon | 2024-01-08 | 1 | 2
Tue | 2024-01-09 | 0 | 0

## Sprint 1 Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2023-11-22 | 5 | 5
Thurs | 2023-11-23 | 4 | 4
Fri | 2023-11-24 | 4 | 4
Sat | 2023-11-25 | 3 | 3
Sun | 2023-11-26 | 3 | 3
Mon | 2023-11-27 | 2 | 2
Tues | 2023-11-28 | 1 | 1
Wed | 2023-11-29 | 1 | 1
Thurs | 2023-11-30 | 1 | 1
Fri | 2023-12-01 | 1 | 1
Sat | 2023-12-02 | 1 | 1
Sun | 2023-12-03 | 1 | 1
Mon | 2023-12-04 | 1 | 1
Tues | 2023-12-05 | 0 | 0
Bold = completed
Velocity 5 tasks assigned and 5 completed.
Tasks 5 - 5 completed. Picture validation below.
Testing
5 completed tasks fully tested and passed.
Screenshots------------------>

## Sprint 1 Planning Backlog
User Story | Tasks | Team Member | Hours Estimated | Hours Actual | NOTE: Can use story points for columns D & E.
As a developer, I want to Contstruct a graphical user interface with a stand-up database. | Create dev environment | Michael | 2 | 2
| Get IDE loaded | All | 8 | 8 | 2 hrs by each team member
| Create project in repository | Michael | 2 | 2
| Install SQL Server Management | All | 4 | 8 | 2 hr by each team member
| Create Database | Tyler & Francisco | 8 | 12 | Tyler 4 hr, Francisco 4 hr, Amsu 4 hr
|  | Total | 24 | 32
|  | Hours/member | 8

## Sprint 1 Demo
Task | By | Accepted | Notes
Create DB environment | Francisco, Tyler | Yes
Download Visual studio | All | Yes
Begin project | Amsu, Michael | Yes
Create repository and upload all source code and database on GitHub | Michael | Yes
Create Discord (CMS) for new communication, ideas, bugs and possible features | Michael | Yes | Daily meetings at 9am (EST) and brain storming
Demo screenshots here

## Sprint 1 Review
Done | Updated | Notes
2023-11-21 | Product backlog updated for new design concepts. | Database is still being created.
2023-12-04 | Sprint one burndown, planning backlog, review, and retrospective. | Database has been completed, uploaded to server and sprint 1 is officially complete.
Velocity consisted of 5 tasks assigned and 5 tasks completed. |  |  | Tasks Assigned | Tasks Completed
|  |  | 5 | 5
Testing
Screenshots
Code
Completed | https://github.com/Youngkeanu94/dreamClock/tree/main/dreamClock
Review of sprint and product |  | The DreamClock is capable of tracking employees' worked hours.The purpose of this sprint was to get that initial project process started. The main five tasks aim to do exactly that as the next sprint the team will add some unique features to the application.

## Sprint 1 Retrospective
What went well? | Improvements? | How?
Development | Communication | Attending scrum meetings.
Scrum meetings | Attendance | Created new discord channel helped members succesfully join the chat
What can be done better in terms of process and not product here | Having a shared drive. | Having a shared drive that allows all of us to work on the files makes it easier to update.

## Sprint 2 Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2023-12-06 | 7 | 7
Thurs | 2023-12-07 | 6 | 7
Fri | 2023-12-08 | 5 | 5
Sat | 2023-12-09 | 5 | 5
Sun | 2023-12-10 | 5 | 5
Mon | 2023-12-11 | 4 | 4
Tues | 2023-12-12 | 3 | 4
Wed | 2023-12-13 | 2 | 3
Thurs | 2023-12-14 | 1 | 3
Fri | 2023-12-15 | 0 | 2
Sat | 2023-12-16 | 0 | 2
Sun | 2023-12-17 | 0 | 2
Mon | 2023-12-18 | 0 | 1
Tues | 2023-12-19 | 0 | 0
Bold = completed
Velocity 7 tasks assigned and 3 completed.
Tasks 7 - 7 completed. Picture validation below.
Code | https://github.com/Youngkeanu94/dreamClock
Testing
Task 7 of 7 completed and fully tested. Picture validation below.
Screenshots------------------>
LoginForm Testing/Demo found here ->https://youtu.be/0YCS_pOBO40

## Sprint 2 Planning Backlog
User Story | Tasks | Team Member | Hours Estimated | Hours Actual | NOTE: Can use story points for columns D & E.
As a user, I want to be able to log in using my employee ID number and my unique password | Create a database table used for tracking the amount of hours employees have worked | Tyler & Francisco | 4 | 4 | 2hr Francisco, 2hr Tyler
| Come up with company standard roles for the database. Such as CEO, HR, Sales, etc. | Tyler & Francisco & Amsu | 8 | 8 | 2hr Amsu, 2hr Tyler, 4hr Francisco
| Create basic login GUI called LoginForm | Michael | 5 | 4
| Give the GUI the appropriate buttons, text boxes and labels. | Amsu | 4 | 4
| Create unique permissions for each unique role in database | Tyler & Francisco | 4 | 8 | 4hr Tyler, 4hr Francisco
| Create login and cancel button on the LoginForm | Michael | 4 | 4
| Upload new code to repository | Michael | 1 | 1
|  | Total | 30 | 33
|  | Hours/member | 8.25

## Sprint 2 Demo
Task | By | Accepted | Notes
Create a database table used for tracking the amount of hours employees have worked | Tyler & Francisco | Yes
Come up with company standard roles for the database. Such as CEO, HR, Sales, etc. | Tyler & Francisco & Amsu | Yes
Create basic login GUI called LoginForm | Michael | Yes
Give the GUI the appropriate buttons, text boxes and labels. | Amsu | Yes
Create unique permissions for each unique role in database | Tyler & Francisco | Yes
Create login and cancel button on the LoginForm | Michael | Yes | Demo found here (same as testing video) --------------> | https://youtu.be/0YCS_pOBO40
Upload new code to repository | Michael | Yes
Demo screenshots here

## Sprint 2 Review
Done | Updated | Notes
2023-11-21 | Product backlog updated for new design concepts. | Database is still being created.
2023-12-04 | Sprint one burndown, planning backlog, review, and retrospective. | Database has been completed, uploaded to server and sprint 1 is officially complete.
2023-12-19 | Sprint 2 planning backlog, burndown, demo, and review | We ran into technical issues when making the GUI and the database. Issues have been resolved but it took more time than expected.
Velocity consisted of 7 tasks assigned and 7 tasks completed. |  |  | Tasks Assigned | Tasks Completed
|  |  | 7 | 7
Testing: All tasks were successfully tested ~ See Sprint burndown 2 for confirmation
Screenshots
Code
Completed | https://github.com/Youngkeanu94/dreamClock
Review of sprint and product |  | This sprint was focused on establishing the application's GUI as well as creating unique roles in the database and permissions for those roles.

## Sprint 2 Retrospective
What went well? | Improvements? | How?
Development | Communication | Delegating tasks more efficiently to avoid confusion.
Team work | Attendance | The teams schedule was conflicting with one another, so removing 1 or 2 scrum meetings a week was the solution.
What can be done better in terms of process and not product here | Having a shared drive. | The team still needs a shared drive. This will make updating/reviewing core documents much easier and add a layer of clarity to what has been done last.

## Sprint 3 Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2023-12-27 | 9 | 9
Thurs | 2023-12-28 | 8 | 8
Fri | 2023-12-29 | 7 | 6
Sat | 2023-12-30 | 7 | 5
Sun | 2023-12-31 | 7 | 5
Mon | 2024-01-01 | 6 | 5
Tues | 2024-01-02 | 5 | 3
Wed | 2024-01-03 | 4 | 3
Thurs | 2024-01-04 | 3 | 3
Fri | 2024-01-05 | 2 | 3
Sat | 2024-01-06 | 2 | 3
Sun | 2024-01-07 | 2 | 2
Mon | 2024-01-08 | 1 | 1
Tues | 2024-01-09 | 1 | 1
Bold = completed
Estimated velocity: 9 tasks. Completed 12 tasks. Adjusting the next sprint's velocity estimate based on this sprint's performance.
Tasks 11 - 9 completed. .
Code | https://github.com/Youngkeanu94/dreamClock
Testing
8 of 9 completed tasks fully tested and passed.
Screenshots------------------> |  |  | Video testing found here:https://www.youtube.com/watch?v=WqNXKBLOFz4

## Sprint 3 Planning Backlog
User Story | Tasks | Team Member | Hours Estimated | Hours Actual | NOTE: Can use story points for columns D & E.
Be able to validate data the user has input and output the appropriate data | Create login method for text box 1 & 2 | Michael | 7 | 2
| Connect the application to the database. | tyler | 1 | 1
| Add MainForm for users to be directed to after successful login | Fransisco, Tyler | 4 | 4 | 2hrs Fransisco, 2hrs Tyler The team discovered a problem during testing mainly with the directory. The MainForm would load after a successful or unsuccessful login and two MainForms were loading at once.
| QA for coding and DB | Fransisco, Michael, Amsu, Tyler | 4 | 2 | Extra task: The team wanted to further discuss how we would implement user stories, if any new features should be added, and where the product currently operates.
| Give the MainForm a datagrid to display data. | Michael | 3 | 2 | Getting the datagrid on the MainForm was easy. However, getting the datagrid to display accurate data was not.
| Add Clock in & Clock out button on the MainForm | Tyler | 1 | 1
| Give the input buttons functionality (Login/Cancel) | Amsu | 4 | 2
| Give Clock in & Clock out buttons functionality | Fransisco, Amsu, Michael | 8 | 8 | 1st half of sprint: 2hrs Francisco, 2hrs Amsu 2nd half of sprint: 3hrs Michael 1hr Francisco Note: The Team had a hard time agreeing on how we should incorporate the functionality, so a lot of work was scrapped and rewritten.
| Conduct unit/integration testing on the Clock in & Clock out buttons | Amsu | 8 | 2 | Had troubles with MSTest and Nunit. Failed task.
| Upload new code to repository | Amsu/Mike | 2 |  | 1st half= Amsu > 1hr 2nd half=Mike >1hr
| Debug Application/Database | Tyler, Francisco | 2 | 7 | Francisco 3hrs Tyler 4hrs Extra task: Bug found when clocking in and out. Some EmployeeIDs and RoleIDs were mismatched causing the clock-in/out to generate the wrong report. Many attempts to correct this were made and is shown in the burndown. Such as altering procedures, adding the EmployeeID to the Login table, and altering the clock-in/out buttons functionality. This is still not fixed.
| Install/ configure Virtual Machine | Amsu | 4 | 2 | Extra task
|  | Total | 48 | 33
|  | Hours/member | 8.25

## Sprint 3 Demo
Task | By | Accepted | Notes
Create login method for text box 1 & 2 | Michael | Yes
Connect the application to the database. | tyler | Yes
Add MainForm for users to be directed to after successful login | Fransisco, Tyler | Yes
QA for coding and DB | Fransisco, Michael, Amsu, Tyler | Yes
Give the MainForm a datagrid to display data. | Michael | Yes
Add Clock in & Clock out button on the MainForm | Tyler | Yes
Give the input buttons functionality (Login/Cancel) | Amsu | Yes
Give Clock in & Clock out buttons functionality | Fransisco, Amsu, Michael | yes
Conduct unit/integration testing on the Clock in & Clock out buttons | Amsu | no | Had a hard time referencing the projects solution in MSTest and Nunit frameworks.
Upload new code to repository | Amsu/Mike | yes | Done twice over the two weeks
Debug Application/Database | Tyler, Francisco | no | This task ended up being a nightmare for the team. First encountering SSL errors
Install/ configure Virtual Machine | Amsu | yes | First two screenshots is our product running on a VM.
Demo found here (same as testing video) --------------> | https://www.youtube.com/watch?v=WqNXKBLOFz4

## Sprint 3 Review
Done | Updated | Notes
2023-11-21 | Product backlog updated for new design concepts. | Database is still being created.
2023-12-04 | Sprint one burndown, planning backlog, review, and retrospective. | Database has been completed, uploaded to server and sprint 1 is officially complete.
2023-12-19 | Sprint 2 planning backlog, burndown, demo, and review. | We ran into technical issues when making the GUI and the database. Issues have been resolved but it took more time than expected.
2024-01-01 | Sprint 3 planning backlog, burndown, demo, and review. | There were some issues getting the clock-in/out function to sync with the DB. Additional tasks added.
2024-01-09 | Sprint 3 burndown, review, retrospective, and the product burndown. | Still having trouble with the clock-in/out button functionality. The problem remains unclear and the team is still searching for a solution. This sprint was the hardest one yet for our team as we encountered underlying issues with the application and the database. This ultimately led to a crazy amount of hours over the sprint.
Estimated Velocity consisted of 9 tasks assigned, 11 tasks were completed and 1 failed. |  |  | Tasks Assigned | Tasks Completed
|  |  | 9 | 11
Testing: 8 tasks successfully tested 1 failed ~ See Sprint burndown 3 for confirmation
Screenshots
Code
Completed | https://github.com/Youngkeanu94/dreamClock
Review of sprint and product |  | This sprint focused on the core functionality of our product. Such as logging in, clocking in/out, and updating to show those new hours by employees. This sprint also brought unexpected trouble for the team as we had to take on more than expected tasks during this sprint. This was arguably the most difficult sprint for us.

## Sprint 3 Retrospective
What went well? | Improvements? | How?
Development | Communication | The holidays made the end of this sprint more difficult than past sprints.
Team work | Attendance | Teams schedule's are still conflicting… again coupled with the holidays it was difficult to wrangle everyone in.
What can be done better in terms of process and not product here | Having a shared drive. | Eight weeks in and we still don't have a shared drive to make our lives easier. Finding an up-to-date backlog can be difficult but not impossible. It just makes the process longer than usual and sometimes confusing.

## Sprint 4 Burndown
Time |  | Tasks
Day | Date | Planned | Actual
Wed | 2024-01-03 | 4 | 4
Thurs | 2024-01-04 | 3 | 4
Fri | 2024-01-05 | 2 | 4
Sat | 2024-01-06 | 2 | 3
Sun | 2024-01-07 | 1 | 3
Mon | 2024-01-08 | 1 | 2
Tues | 2024-01-09 | 0 | 0
Bold = completed
Velocity 4 tasks assigned and 4 completed.
Tasks 4 - 4 completed.
Code > https://github.com/Youngkeanu94/dreamClock
Testing
4 completed tasks fully tested and passed. |  |  |  | Video testing/demo > https://www.youtube.com/watch?v=7m4dp_Myxeo
Screenshots------------------>

## Sprint 4 Planning Backlog
User Story | Tasks | Team Member | Hours Estimated | Hours Actual | NOTE: Can use story points for columns D & E.
As a developer. I would like to confirm the application is running efficiently and is effective | Test overall functionality of the application | Tyler | 2 | 1
| Revise/Refine the applications code | Amsu | 4 | 5
| Debug | Michael, Tyler, Francisco | 4 | 10 | 4hr Michael, 2hr Tyler, 4hr Francisco
| Upload code to repository | Tyler | 1 | 1
|  | Total | 11 | 17
|  | Hours/member | 4.25

## Sprint 4 Demo
Task | By | Accepted | Notes
Test overall functionality of the application | Tyler | Yes
Revise/Refine the applications code | Amsu | Yes
Debug | Michael, Tyler, Francisco | Yes | Became more of a team effort and took longer than anticipated
Upload code to repository | Tyler | Yes
Daily meetings at 9am (EST) and brain storming
https://www.youtube.com/watch?v=7m4dp_Myxeo | <-- Same video on burndown
Demo screenshots here

## Sprint 4 Review
Done | Updated | Notes
2023-11-21 | Product backlog updated for new design concepts. | Database is still being created.
2023-12-04 | Sprint one burndown, planning backlog, review, and retrospective. | Database has been completed, uploaded to server and sprint 1 is officially complete.
2023-12-19 | Sprint 2 planning backlog, burndown, demo, and review. | We ran into technical issues when making the GUI and the database. Issues have been resolved but it took more time than expected.
2024-01-01 | Sprint 3 planning backlog, burndown, demo, and review. | There were some issues getting the clock-in/out function to sync with the DB. Additional tasks added.
2024-01-09 | Sprint 3 burndown, review, retrospective, and the product burndown. | Still having trouble with the clock-in/out button functionality. The problem remains unclear and the team is still searching for a solution. This sprint was the hardest one yet for our team as we encountered underlying issues with the application and the database. This ultimately led to a crazy amount of hours over the sprint.
2024-01-16 | Sprint 4 burndown, review, demo retrospective, and the product burndown. | The code was revised/refined. Debugging was a challenge. Overall, successful sprint
Estimated Velocity consisted of 4 tasks assigned, 4 tasks were completed |  |  |  | Tasks Assigned | Tasks Completed
|  |  |  | 4 | 4
Testing: 4 tasks successfully tested ~ See Sprint burndown 4 for confirmation
Screenshots
Code
Completed | https://github.com/Youngkeanu94/dreamClock | Application Demo/testing > https://www.youtube.com/watch?v=7m4dp_Myxeo | Database Review> https://youtu.be/6e9O7untWck
Review of sprint and product |  | The final sprint's main focus was putting the finishing touches on the application and working out some know bugs for optimal performance

## Sprint 4 Retrospective
What went well? | Improvements? | How?
Development | Communication | Be more active
Team work | Attendance | Configure a new time for meetings
What can be done better in terms of process and not product here | Never had a shared drive. | Start/share excel workbook with team members.